## Setup
PROJECT SETUP
Business Name:
Project Name:
Project Address:
Client Name:
Contract Number:
Start Date:
Completion Date:
Site Supervisor:

## Program
CONSTRUCTION PROGRAM
Project: |  |  | Contract completion:
ID | Task | Trade | Start | Duration (working days) | Finish | Predecessor ID | % Complete | Notes
1 | Site establishment
2 | Set out and excavation |  |  |  |  | 1
3 | Footings and slab |  |  |  |  | 2
4 | Frame |  |  |  |  | 3
5 | Roof cover |  |  |  |  | 4
6 | Windows and external doors (lock-up) |  |  |  |  | 5
7 | Rough-in: plumbing, electrical, mechanical |  |  |  |  | 6
8 | Insulation |  |  |  |  | 7
9 | Plasterboard |  |  |  |  | 8
10 | Waterproofing |  |  |  |  | 9
11 | Fix-out: joinery, doors, trims |  |  |  |  | 10
12 | Tiling |  |  |  |  | 11
13 | Painting |  |  |  |  | 12
14 | Fit-off: plumbing, electrical |  |  |  |  | 13
15 | External works and landscaping |  |  |  |  | 14
16 | Final clean |  |  |  |  | 15
17 | Practical completion inspection |  |  |  |  | 16
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## Holidays
NON-WORKING DAYS
Date | Reason

## Instructions
HOW TO USE THIS WORKBOOK
STEP 1: | Fill in Setup. The Start Date is the first day on site.
STEP 2: | On Holidays, list public holidays, the industry shutdown (RDOs if you take them) and any other non-working days for the job's state.
STEP 3: | On Program, list tasks in order. Give each a duration in working days. Put the ID of the task it follows in Predecessor ID and the start and finish dates calculate themselves; leave Predecessor ID blank and type a Start date for a task that doesn't follow another.
STEP 4: | The bars show each task against week-commencing dates. Update % Complete each week.
STEP 5: | If the program slips past the contract completion date, issue a Delay Notification for any delay you are entitled to an extension of time for.